## 📋 Overview
🎮 SCHIZO SHADOWS ¦ FYP3 PROJECT PLAN
February 2026 → April 2026 ¦ Team: Waleed, Momina, Muqadas
STATUS LEGEND |  | PHASE | WEEKS | DATES | FOCUS | STATUS
✅ Done |  | Phase 0 – Polish Act 1 | Wk 1-2 | Feb 19 – Mar 1 | Bug fixes, UI, save system | ❌ Not Started
🔄 In Progress |  | Phase 1 – Act 2 Build | Wk 3-5 | Mar 2 – Mar 20 | Backrooms level + new ghost | ❌ Not Started
❌ Not Started |  | Phase 2 – Act 3 Build | Wk 6-7 | Mar 21 – Apr 3 | Final area + boss scare | ❌ Not Started
⏸ Blocked |  | Phase 3 – Integration | Wk 8 | Apr 4 – Apr 10 | All acts connected, endings | ❌ Not Started
|  | Phase 4 – Testing & Submit | Wk 9-10 | Apr 11 – Apr 25 | Playtesting, bug fix, submit | ❌ Not Started
🏆 KEY MILESTONES
DATE | MILESTONE DESCRIPTION
Mar 1 | Act 1 fully polished, no critical bugs
Mar 20 | Act 2 (Backrooms) playable end-to-end
Apr 3 | Act 3 complete with boss jumpscare
Apr 10 | Full game loop with multiple endings working
Apr 18 | Final playtesting complete, no P1 bugs
Apr 25 | Submission ready – build + documentation
📊 PROGRESS TRACKER (auto-calculated from Task Sheet)
METRIC | VALUE | NOTES
Total Tasks | -90 | All tasks in tracker
✅ Completed | 0 | Auto-updates from Task sheet
🔄 In Progress | 0
❌ Not Started | 0
% Complete | 0%
Days Until Deadline | 65 | Target: Apr 25, 2026

## 📅 Weekly Plan
📅 WEEK-BY-WEEK DEVELOPMENT PLAN ¦ SCHIZO SHADOWS FYP3
WEEK | GOALS / DELIVERABLES | TASKS | OWNER | STATUS
⚡ PHASE 0 – ACT 1 POLISH
Week 1 Feb 19–23 | Fix all Act 1 bugs Add Main Menu polish | • Fix ghost clipping through doors • Fix sanity UI alignment in VR • Main menu scene polish • Add settings (volume, turn type) • Scene transition fade working | All | ❌ Not Started
Week 2 Mar 1 | Save system + final Act 1 QA Milestone: Act 1 LOCKED | • PlayerPrefs save for settings • Add credits screen • Final Act 1 playthrough (no breaks) • Fix any remaining P1 bugs • ✅ ACT 1 MILESTONE | Waleed | ❌ Not Started
⚡ PHASE 1 – ACT 2: BACKROOMS
Week 3 Mar 2–8 | Build Backrooms level geometry MemoryFragment system | • Design & block out Backrooms maze • Add neon light flicker atmosphere • Create MemoryFragment prefab • Place 3 fragments in scene • ExitDoor locks until all collected | Momina | ❌ Not Started
Week 4 Mar 9–15 | New ghost for Act 2 Sanity tuning | • Create Act 2 ghost (GhostHunter variant) • Different hunt pattern (faster, no warning) • Sanity drain zones in Backrooms • HorrorAudioController – new ambient sounds • VR interaction for memory fragments | Muqadas | ❌ Not Started
Week 5 Mar 16–20 | Act 2 endings + integration Milestone: Act 2 playable | • Multiple endings logic (sanity based) • SceneTransitionManager → Act 3 • Full Act 2 playthrough test • Fix framerate & performance • ✅ ACT 2 MILESTONE | All | ❌ Not Started
⚡ PHASE 2 – ACT 3: FINALE
Week 6 Mar 21–27 | Act 3 environment Boss ghost system | • Design final area (asylum/mind space) • Boss ghost: multi-phase FSM • Phase 1: stalking (like Act 1) • Phase 2: teleporting short range • Phase 3: all-out hunt – no escape | Waleed + Momina | ❌ Not Started
Week 7 Mar 28–Apr 3 | Climax jumpscare + endings Milestone: Act 3 complete | • Final boss jumpscare sequence • 2 endings: escape OR caught • End credits sequence • Full Act 3 playthrough • ✅ ACT 3 MILESTONE | Muqadas | ❌ Not Started
⚡ PHASE 3 – INTEGRATION
Week 8 Apr 4–10 | Stitch all 3 acts together Milestone: Full game loop | • Act 1 → 2 → 3 transition working • Sanity carries across acts • Consistent UI/UX across all scenes • Settings persist game-wide • Full playthrough: start to credits • ✅ FULL GAME MILESTONE | All | ❌ Not Started
⚡ PHASE 4 – TESTING & SUBMIT
Week 9 Apr 11–17 | Playtesting sprint Bug triage | • 3 full playthroughs each teammate • Log all bugs in Bug Tracker sheet • Fix P1 (game-breaking) bugs • Sound mixing pass • VR comfort pass (no motion sickness) | All | ❌ Not Started
Week 10 Apr 18–25 | Final polish + SUBMISSION Milestone: SUBMITTED ✅ | • Fix remaining P2 bugs • Final build export (PC VR) • Record gameplay demo video • Update FYP documentation • Submit to supervisor • 🎉 DONE! | All | ❌ Not Started

## 📝 Task Tracker
📝 TASK TRACKER ¦ SCHIZO SHADOWS FYP3
# | TASK | PHASE / ACT | WEEK | PRIORITY | STATUS | NOTES
── PHASE 0: ACT 1 POLISH ──
1 | Fix ghost clipping through locked doors | Act 1 | Week 1 | 🔴 P1 Critical | ❌ Not Started
2 | Fix sanity UI slider alignment in VR headset | Act 1 | Week 1 | 🟠 P2 High | ❌ Not Started
3 | Main menu UI polish – add logo, background art | Act 1 | Week 1 | 🟡 P3 Medium | ❌ Not Started
4 | Settings menu – volume slider, turn type toggle | Act 1 | Week 1 | 🟠 P2 High | ❌ Not Started
5 | Scene transition fade working (Act 1 → next) | Act 1 | Week 1 | 🔴 P1 Critical | ❌ Not Started
6 | Save settings with PlayerPrefs | Act 1 | Week 2 | 🟠 P2 High | ❌ Not Started
7 | Add credits screen | Act 1 | Week 2 | 🟢 P4 Low | ❌ Not Started
8 | Full Act 1 playthrough QA – document all bugs | Act 1 | Week 2 | 🔴 P1 Critical | ❌ Not Started
9 | ACT 1 MILESTONE SIGN-OFF ✅ | Act 1 | Week 2 | 🔴 P1 Critical | ❌ Not Started
── PHASE 1: ACT 2 BACKROOMS ──
10 | Block out Backrooms maze level geometry in Unity | Act 2 | Week 3 | 🔴 P1 Critical | ❌ Not Started
11 | Add neon flicker lights & horror atmosphere lighting | Act 2 | Week 3 | 🟠 P2 High | ❌ Not Started
12 | Create MemoryFragment prefab (VR grabbable + glow) | Act 2 | Week 3 | 🔴 P1 Critical | ❌ Not Started
13 | Place 3 memory fragments in scene | Act 2 | Week 3 | 🔴 P1 Critical | ❌ Not Started
14 | ExitDoor locks until all 3 fragments collected | Act 2 | Week 3 | 🔴 P1 Critical | ❌ Not Started
15 | Create Act 2 ghost variant (GhostHunter – faster) | Act 2 | Week 4 | 🔴 P1 Critical | ❌ Not Started
16 | No HuntWarning state – immediate hunt on sight | Act 2 | Week 4 | 🟠 P2 High | ❌ Not Started
17 | Sanity drain zones placed in Backrooms corridors | Act 2 | Week 4 | 🟠 P2 High | ❌ Not Started
18 | New ambient horror audio set for Backrooms | Act 2 | Week 4 | 🟡 P3 Medium | ❌ Not Started
19 | VR interaction for memory fragment pickup | Act 2 | Week 4 | 🔴 P1 Critical | ❌ Not Started
20 | Implement multiple endings based on sanity level | Act 2 | Week 5 | 🟠 P2 High | ❌ Not Started
21 | SceneTransitionManager → Act 3 working | Act 2 | Week 5 | 🔴 P1 Critical | ❌ Not Started
22 | Performance pass – maintain 72fps in VR | Act 2 | Week 5 | 🟠 P2 High | ❌ Not Started
23 | ACT 2 MILESTONE SIGN-OFF ✅ | Act 2 | Week 5 | 🔴 P1 Critical | ❌ Not Started
── PHASE 2: ACT 3 FINALE ──
24 | Design & build final environment (asylum/mind space) | Act 3 | Week 6 | 🔴 P1 Critical | ❌ Not Started
25 | Boss ghost FSM – Phase 1: Stalking (like Act 1 ghost) | Act 3 | Week 6 | 🔴 P1 Critical | ❌ Not Started
26 | Boss ghost FSM – Phase 2: Short-range teleporting | Act 3 | Week 6 | 🔴 P1 Critical | ❌ Not Started
27 | Boss ghost FSM – Phase 3: All-out hunt, no escape | Act 3 | Week 6 | 🔴 P1 Critical | ❌ Not Started
28 | Sanity triggers boss phase transitions | Act 3 | Week 6 | 🟠 P2 High | ❌ Not Started
29 | Final boss jumpscare sequence (extended version) | Act 3 | Week 7 | 🔴 P1 Critical | ❌ Not Started
30 | Ending A: Player escapes – cut scene / credits | Act 3 | Week 7 | 🟠 P2 High | ❌ Not Started
31 | Ending B: Player caught – unique game over | Act 3 | Week 7 | 🟠 P2 High | ❌ Not Started
32 | End credits rolling sequence | Act 3 | Week 7 | 🟡 P3 Medium | ❌ Not Started
33 | ACT 3 MILESTONE SIGN-OFF ✅ | Act 3 | Week 7 | 🔴 P1 Critical | ❌ Not Started
── PHASE 3: INTEGRATION ──
34 | Act 1 → Act 2 → Act 3 scene flow working | Integration | Week 8 | 🔴 P1 Critical | ❌ Not Started
35 | Sanity value persists / resets correctly between acts | Integration | Week 8 | 🔴 P1 Critical | ❌ Not Started
36 | Consistent HUD / UI across all 3 acts | Integration | Week 8 | 🟠 P2 High | ❌ Not Started
37 | Settings persist across entire game session | Integration | Week 8 | 🟠 P2 High | ❌ Not Started
38 | Full playthrough: main menu → credits | Integration | Week 8 | 🔴 P1 Critical | ❌ Not Started
39 | FULL GAME LOOP MILESTONE ✅ | Integration | Week 8 | 🔴 P1 Critical | ❌ Not Started
── PHASE 4: TESTING & SUBMIT ──
40 | Playtesting round 1 – each member plays full game | QA | Week 9 | 🔴 P1 Critical | ❌ Not Started
41 | Log all bugs in Bug Tracker sheet | QA | Week 9 | 🔴 P1 Critical | ❌ Not Started
42 | Fix all P1 (game-breaking) bugs | QA | Week 9 | 🔴 P1 Critical | ❌ Not Started
43 | Sound mixing pass – balance ambient, SFX, music | QA | Week 9 | 🟡 P3 Medium | ❌ Not Started
44 | VR comfort pass – no motion sickness triggers | QA | Week 9 | 🟠 P2 High | ❌ Not Started
45 | Fix remaining P2 high-priority bugs | QA | Week 10 | 🟠 P2 High | ❌ Not Started
46 | Final build export for PC VR | QA | Week 10 | 🔴 P1 Critical | ❌ Not Started
47 | Record gameplay demo video (5-10 min) | QA | Week 10 | 🟠 P2 High | ❌ Not Started
48 | Update FYP3 documentation & report | QA | Week 10 | 🔴 P1 Critical | ❌ Not Started
49 | SUBMIT TO SUPERVISOR 🎉 | QA | Week 10 | 🔴 P1 Critical | ❌ Not Started

## 🐛 Bug Tracker
🐛 BUG TRACKER ¦ SCHIZO SHADOWS FYP3
# | ACT | BUG DESCRIPTION | STEPS TO REPRODUCE | PRIORITY | STATUS | ASSIGNED TO | DATE FOUND
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19

## ✅ Feature Checklist
✅ FEATURE CHECKLIST ¦ SCHIZO SHADOWS FYP3
FEATURE | ACT | DONE? | NOTES
── CORE SYSTEMS ──
Ghost AI (FSM – 6 states) | All Acts | ✅
Sanity System (drain / restore) | All Acts | ✅
VR Hand Physics | All Acts | ✅
Audio Manager (Singleton) | All Acts | ✅
Scene Transition with Fade | All Acts | ✅
Safe Room System | Act 1 | ✅
Key & Door Lock System | Act 1 | ✅
Jumpscare Sequence | Act 1 | ✅
Horror Ambient Audio | Act 1 | ✅
Flicker Lights | Act 1 | ✅
Readable Notes / Clues | Act 1 | ✅
Main Menu | Menu | ✅
── ACT 2 FEATURES (TO BUILD) ──
Backrooms Level Design | Act 2 | ❌
MemoryFragment System (3 collectibles) | Act 2 | ❌
ExitDoor Fragment-Lock | Act 2 | ❌
Faster Ghost Variant (no warning) | Act 2 | ❌
Multiple Endings (sanity-based) | Act 2 | ❌
New Ambient Sound Pack | Act 2 | ❌
── ACT 3 FEATURES (TO BUILD) ──
Final Environment (Asylum) | Act 3 | ❌
Boss Ghost – 3-Phase FSM | Act 3 | ❌
Boss Ghost Teleport Mechanic | Act 3 | ❌
Extended Boss Jumpscare | Act 3 | ❌
Ending A: Escape Cut Scene | Act 3 | ❌
Ending B: Caught Game Over | Act 3 | ❌
Rolling End Credits | Act 3 | ❌
── INTEGRATION & POLISH ──
Act 1 → 2 → 3 Flow | All | ❌
Sanity Persistence Between Acts | All | ❌
Consistent UI Across All Acts | All | ❌
Settings Persist Game-Wide | All | ❌
Performance: 72fps VR Target | All | ❌
Sound Mixing Pass | All | ❌
VR Comfort Pass | All | ❌
Gameplay Demo Video | Submit | ❌
FYP Documentation Updated | Submit | ❌